## Slide 1: Mid Phase review
Project Management

## Slide 2: What has been done/completed?
Original plan was completed, PID feedback was given
Communication meetings established
  Bi-weekly meetings with David
  End of week meetings with Rob Miles + Rob Finnis
  Review sessions put in place
Gantt chart updated periodically
Technical work
  Looked at methods to add visual feedback for the states of machine (going to recycle a program done last year)
  Supported on motors – initial testing, obtaining power supply

## Slide 3: Any problems so far
Material procurement has delayed tasks
Getting required training has delayed manufacturing
Found additional risks as we have needed additional equipment
Still unable to calculate required battery size, until further testing

## Slide 4: What are the next steps
Currently under a full plan review which is being informed by current progress and feedback from the PID and teams working styles
Conducting more research on how projects run in industry
Technical
  Designing circuit which will integrate for the LEDs
  Establish method of communicating with the other programs what state the robot is in

## Slide 5: Problems likely to occur
Communication (a given for any team)
Manufacturing delays
Product procurement
Technical
  Being unable to test under load
    Delay of wheels for directional control and load bearing